## Summary for Sponsors
Scope Category | Funding Source | KPIF 2023 Allocation | Forecast through July | ETC (Estimate to Complete) | EAC (Estimate at Completion) | Variance | Conf. Level | Comments
|  | (A) | (B) | (C) | (D=B+C)
Run and Manage (2024 Go-to-Market) | KPIF/PAC | 5530 | 5606 | 2663 | 8269 | -2739 | Medium (Product Roadmap)
Automate Web Based Broker Application Submission | KPIF/PAC | 200 | 73 | 0 | 73 | 127 | High (Iteration) | Expand automated application submission from Web Based Brokers: eHealth and QuotIt
Paperless Delivery for KPIF Correspondences | KPIF/PAC | 199 | 42 | 121 | 163 | 36 | Medium (Product Roadmap) | Completion of the product vision phase resulted a higher LOE from EPP systems
Enhanced Direct Enrollment Single Sign On | KPIF/PAC | 120 | 32316 | 80 | 32396 | -32276 | High (Iteration) | Complete Single Sign On testing and implementation for National Consumer Sales. Continuation of work started in 2022.
Create Online Spanish-Language Application Experience | KPIF/PAC | 500 | 294 | 145 | 439 | 61 | Medium (Product Roadmap) | Spanish Decision Letters deferred to 2024. Included in 2024 MYP
Other CRs and Enhancements | KPIF/PAC | 280 | 7 | 170 | 177 | 103 | Medium (Product Roadmap) | Business to prioritize Compliance/Regulatory and consumer experience improvement needs.
Total |  | 6829 | 38338 | 3179 | 41517 | -34688
Funding Source | Amount
1X from Board | 870 | KPIF systems abc ID
CCPE ($830K) other systems | 830 | CCPE ABC id
CCPE ($400) BCSSP KPD | 400
2100
2583

## PM Assignment
KPIF Systems 2023 | Budget | PM assigned
KPIF Systems VS1 (OE) | 3000000 | Naser | Funded
KPIF Systems VS2 ( SEP+ SEE) | 2000000 | Niru | Funded
KPIF Systems VS3 CRs | 2000000 | Jason | Funded
KPIF Systems 2023 Total | 7000000
Other KPIF Integration Projects
KPMC DI -VS 3 | 500000 | Tejas | Funded
KPMC DI -VS 2-3 | 250000 | Saravana | Funded
KPMC QIR | 176000 | Saravana | Funded
KPWA | 85000 | Saravana | Funded
ALM SMU | 972000 | Phanee | Funded
ILM SMU | 147000 | Phanee | Funded
EDE | 120000 | Sachin | Funded
Broker Self-Service (1x) | 870000 | Raja | Funded
Broker Self-Service (CCPE) | 1230000 | Sachin | Funded
JKP-SEE | 200000 | Niru | Pending
KPIF Systems Integration Total | 4550000
Grand Total | 11550000
Naser | FTE
Niru | FTE
Jason | FTE
Raja | TCS
Tejas | TCS
Saravana | TCS
Phanee | TCS
Sachin Dager | TCS

## KPIF funding
Program/Project |  | 2021 Forecast | 2023 IT Forecast | 2023 Preliminary Approved |  | Funding Source | Comments | IT Remaining Forecast | IT Actual + Forecast | IT Variance | 2023 Business Allocation | Business Drivers | Funding Source (PAC/BCD) |  | Key Scope / Description
| Go-Live date |  |  |  | GAP Pending |  |  |  |  | (Budget to Forecast) |  |  |  | LOP
KPIF Systems 2023 (Go-To -Market)
OPEN ENROLLMENT | 2023-11-01 | 3.2 | 3.85 | 3.85 | 0 | PAC |  | 3.85 | 3.85 | 0 | 0.7 | Regulatory / Compliance | PAC | 4.55 | Go-to-market changes for 2024 Open Enrollment (/Joining KP 2.0, Sign Me Up, Application Management Tool)
RENEWALS | 2023-06-30 | 0.58 | 0.79 | 0.79 | 0 | PAC |  | 0.79 | 0.79 | 0 | 0 | Regulatory / Compliance | PAC | 0.79 | Membership renewal for KPIF systems 2024
Non OE Priorities (SEP) | 2023-06-30 | 0.66 | 0.79 | 0.79 | 0 | PAC |  | 0.79 | 0.79 | 0 | 0 | Regulatory / Compliance | PAC | 0.79 | Required Regulatory and Compliance Priorities
Adobe Tagging and A/B testing | 2023-06-30 | 0.43 | 0.1 | 0.1 |  | PAC |  | 0.1 | 0.1 |  |  |  |  | 0.1
KPIF Systems 2023 (Go-To -Market) Subtotal |  | 4.87 | 5.53 | 5.53 | 0 |  | 0 | 5.53 | 5.53 | 0 | 0.7 |  |  | 6.23
KPIF System Enhancements
Automate Web Based Broker Application Submission | 2023-10-30 |  | 0.2 | 0.2 |  | PAC |  | 0.2 | 0.2
Paperless Delivery for KPIF Correspondences | 2023-10-30 |  | 0.2 | 0.2 | 0 | PAC |  | 0.2 | 0.2 |  |  |  | PAC | 0.2
Enhanced Direct Enrollment Single Sign On | 2023-10-30 |  | 0.12 | 0.12 |  | PAC |  | 0.12 | 0.12
SMU in Spanish | 2023-10-30 |  | 0.5 | 0.5 |  | PAC |  | 0.5 | 0.5 | [5 empty] | Tina confrimed KPIF will pay for this project
Other CRs | 2023-10-30 |  | 0.28 | 0.28 |  | PAC |  | 0.28 | 0.28
KPIF Systems Enhancements Subtotal |  |  | 1.3 | 1.3 | 0 | 0 | 0 | 1.3 | 1.3 | 0 | 0 | 0 | 0 | 0.2
KPIF Systems 2023 Total |  |  | 6.83 | 6.83 | 0 | 0 | 0 | 6.83 | 6.83 | 0 | 0.7 | 0 | 0 | 6.43 | PAC approved $8.3M as of 12/18/2022
KPIF Broker Self Service
KPIF Broker Self Service tool ( $830+$400) | 2023-10-30 |  | 1.23 | 1.23 | 0 | KPD |  | 1.23 | 1.23 | [5 empty] | Pening Prioritization amount and RPM
KPIF Broker Self Service tool ( 1X) | 2023-10-30 |  | 0.87 | 0.87 |  | 1X |  | 0.87 | 0.87
KPIF Broker Self Service Subtotal |  |  | 2.1 | 2.1 | 0 | 0 | 0 | 2.1 | 2.1
KPMC Integrations
Data Integration (DI) | 2023-06-30 |  | 0.55 | 0.55 | 0 | KPMC |  | 0.55 | 0.55 |  |  |  | KPMC | 0.55 | Gabriel confirmed $750K
QIR Broker | 2023-06-30 |  | 0.176 | 0.176 | 0 | KPMC |  | 0.176 | 0.176 |  |  |  | KPMC | 0.176 | Manoj and raja confirmed $176K
KPWA | 2023-03-20 | 1.371 | 0.2 | 0.2 | 0 | KPMC |  | 0.2 | 0.2 |  |  |  | KPWA/KPMC | 1.571 | Gabriel confirmed
KPMC Integrations Subtotal |  |  | 0.926 | 0.926 | 0 | 0 | 0 | 0.726 | 0.726 | 0 | 0
Other KPIF initiatives
JKP KPIF (Medicaid) | 2023-07-21 | 0.73 | 0.2 |  | -0.2 | JKP |  | 0.2 | 0.2 |  |  |  | KPD | 0.93
SMU Scrub | 2023-11-01 |  | 0.105 |  | -0.105 |  |  | 0.105 | 0.105 | [5 empty] | Pending funding from MA (might move to 2024)
Other KPIF initiatives Subtotal |  |  | 0.305 | 0 | -0.305 |  | #REF! | 0.305 | 0.305 | 0 | 0 | #REF! | #REF!
ALMs and Infrastructure
SMU ALM | 2023-08-22 |  | 0.97 | 0.97 | 0 | ALM |  | 0.97 | 0.97 |  |  | ALM | ALM
AMT ALM (server refresh) | 2023-07-23 |  | 0.132 | 0.132 |  | ALM
SMU ILM | 2023-08-22 |  | 0.147 | 0.147 |  | ILM |  | 0.147 | 0.147
ALMs and Infrastructure Subtotal |  |  | 1.249 | 1.249 | 0 | 0 | 0 | 1.117 | 1.117 | 0 | 0 |  | ALM
KPIF Portfolio 2023 Totals |  |  | 11.41 | 11.105 | -0.305 | 0 | #REF! | 11.078 | 11.078 | 0 | 0.7 | #REF! | #REF! | 6.43
2.2

## Sheet2
Scope Category | Funding Source | KPIF 2023 Allocation | Actuals through May | ETC (Estimate to Complete) | EAC (Estimate at Completion) | Variance | Conf. Level | Comments
|  | (A) | (B) | (C) | (D=B+C)
Run and Manage (2024 Go-to-Market) | KPIF/PAC | 5530 | 1973 | 3557 | 5530 | 0 | Medium (Product Roadmap)
Automate Web Based Broker Application Submission | KPIF/PAC | 200 | 72 | 128 | 200 | 0 | High (Iteration) | Expand automated application submission from eHealth for all regions (except HI); currently only CA has this capability.
Paperless Delivery for KPIF Correspondences | KPIF/PAC | 200 | 28 | 227 | 255 | -55 | Medium (Product Roadmap) | Completion of the product vision phase resulted a higher LOE from EPP systems
Enhanced Direct Enrollment Single Sign On | KPIF/PAC | 120 | 105 | 15 | 120 | 0 | High (Iteration) | Complete Single Sign On testing and implementation for National Consumer Sales. Continuation of work started in 2022.
Create Online Spanish-Language Application Experience | KPIF/PAC | 500 | 195 | 205 | 400 | 100 | Medium (Product Roadmap) | Spanish Decision Letters deferred to 2024. Included in 2024 MYP
Other CRs and Enhancements | KPIF/PAC | 280 | 40 | 285 | 325 | -45 | Medium (Product Roadmap) | Business to prioritize Compliance/Regulatory and consumer experience improvement needs.
KPIF/PAC Sub-Total |  | 6830 | 2413 | 4417 | 6830 | 0
5
2418
4836

## detail view
Scope Category | Funding Source | KPIF 2023 Allocation | Actuals through April | ETC (Estimate to Complete) | EAC (Estimate at Completion) | Variance | Conf. Level | Comments
|  | (A) | (B) | (C) | (D=B+C)
2024 Go-to-Market: Open Enrollment (OE) | KPIF/PAC | 3950 | 526 | 3424 | 3950 | 0 | Medium (Product Roadmap)
2024 Go-to-Market: Renewal | KPIF/PAC | 790 | 655 | 135 | 790 | 0 | Medium (Product Roadmap)
2024 Go-to-Market: Non OE Regulatory and Compliances | KPIF/PAC | 790 | 343 | 447 | 790 | 0 | Medium (Product Roadmap)
Run and Manage (2024 Go-to-Market) Sub-Total |  | 5530 | 1524 | 4006 | 5530 | 0
Other CRs and Enhancements | KPIF/PAC | 280 | 15 | 310 | 325 | -45 | Medium (Product Roadmap) | Business to prioritize Compliance/Regulatory and consumer experience improvement needs.
Automate Web Based Broker Application Submission | KPIF/PAC | 200 | 72 | 128 | 200 | 0 | High (Iteration) | Expand automated application submission from eHealth for all regions (except HI); currently only CA has this capability.
Paperless Delivery for KPIF Correspondences | KPIF/PAC | 200 | 28 | 227 | 255 | -55 | Medium (Product Roadmap) | Provide applicants the ability to select a paperless correspondence option for invoices and renewal notifications while applying online.
Enhanced Direct Enrollment Single Sign On | KPIF/PAC | 120 | 96 | 24 | 120 | 0 | High (Iteration) | Complete Single Sign On testing and implementation for National Consumer Sales. Continuation of work started in 2022.
Create Online Spanish-Language Application Experience | KPIF/PAC | 500 | 122 | 278 | 400 | 100 | Medium (Product Roadmap) | To improve the percentage of Spanish-language applicants that complete an application online.
Non Run and Manage Sub-Total |  | 1300 | 333 | 967 | 1300 | 0
2023 KPIF/PAC funded 2023 Total |  | 6830 | 1857 | 4973 | 6830 | 0 | 0
KPIF Broker Self-Service | 1X | 870 | 0 | 870 | 870 | 0 | Medium (Product Roadmap) | KPIF business confirmed we will utilize $870K 1X funding to support the program.
KPIF Broker Self-Service CCPE | CCPE | 1230 | 35 | 1195 | 1230 | 0 | Medium (Product Roadmap) | CCPE will contribute up to $1,230K
Total |  | 8930 | 1892 | 7038 | 8930 | 0 | 0

## PM Back-Up proposal
Back up plan
| Items | Primary Back Up | 2ndary Back up
Niru | SMU Spanish | Jason | Tejas
| Pilot until 5/31 | Tejas | Jason
Jason | Intake | Niru | TBD
| Overall budget | Niru | Intern
Raja | Broker | Jason ( 6/15-7/14)
| KPMC DI Hawaii | Saravana | Phanee
Tejas | Renewal | Niru | Jason
| Open Enrollment | Niru | Jason
Saravana | EDE | Jason | Phanee
| eHealth/Take Command | Jason | Phanee
Phanee | ALMs | Jason
Sachin Dager | DEVops

## PM cost
|  | PM budget at 13% | PM budget at 15% | PM budget at 18%
KPIF Systems 2023 Total
KPIF Systems VS1 (OE) | 3000000 | 390000 | 450000 | 540000 | funded
KPIF Systems VS2 ( SEP+ SEE) | 2000000 | 260000 | 300000 | 360000 | funded
KPIF Systems VS3 CRs | 2000000 | 260000 | 300000 | 360000 | funded
KPIF Systems 2023 Total | 7000000 | 910000 | 1050000 | 1260000 | funded
Other KPIF Integration Projects
KPMC DI -VS 3 | 500000 | 65000 | 75000 | 90000 | funded
KPMC DI -VS 2-3 | 250000 | 32500 | 37500 | 45000 | funded
KPMC QIR | 176000 | 22880 | 26400 | 31680 | funded
ALM SMU | 972000 | 126360 | 145800 | 174960 | funded
ALM AMT | 130000 | 16900 | 19500 | 23400 | funded
EDE | 120000 | 15600 | 18000 | 21600 | funded
Broker Self-Service (KPD+1X) | 2030000 | 263900 | 304500 | 365400 | funded
SMU NCS ( 5/17) | 68000 | 8840 | 10200 | 12240 | funded
JKP-SEE | 200000 |  | 0 | 0 | Pending
KPIF Systems Integration Total | 4446000 | 551980 | 636900 | 764280
Grand Total | 11446000 | 1461980 | 1686900 | 2024280
PM Annual cost at 85%
Naser | 184 |  | 325312
Niru | 141 |  | 249288
Jason | 141 |  | 249288
Raja | 101.8 |  | 179982.4
Tejas | 101.8 |  | 179982.4
Saravana | 101.8 |  | 179982.4
Phanee | 101.8 |  | 89991.2 | 50% charging to Marketing ALM
Sachin | 101.8 |  | 142520 | will not start until March
1596346.4

## Sheet1
Category | HLOE | OE | Non Regulatory | Renewal | SMU Spainsih | Wbe | paperless | EDE | CRs
Budget |  | 3950 | 790 | 790 | 500 | 200 | 200 | 120 | 280 | 6830
Spent |  | 310 | 278 | 510 | 60 | 72 | 26 | 77 |  | 1333 | 2023-03-21
Remaining |  | 3640 | 512 | 280 | 440 | 128 | 174 | 43 | 280 | 5497
100
Unfunded work
RM1064/2023.10142024 NW WA On Exchange Family Dental Plans-OE | 0
RM1087/KPWA Plan Name vs Product Type Switc
RM1068/Virginia transition to state-based exchange | 40
RM1081/2023.1022SEP Reminder Emails for Phone App | 75
RM1088/AMT Welcome letter display previous attribute changes
RM1056/JKP Subsidy Expansion (NCS Support) | 50
RM1070/Q4 Applicants Messaging/ Plan Display -2023 Work
RM1067/MAS HMO Plus Product Launch (MD, DC) | 50
RM1061/GA Medicaid Expansion ( Paid by region)
RM 1034 / 2022.1085 | 40
RM1035/2022.1096Plan Template change for OE 2024 | 18
RM1082/2023.1023 JKP - CO - HIAE CSR 94 Enhancement to expand to 150-250% | 2
RM637/2022.1047SMU – Customizable Urgency Messaging | 60
RM680/SMU Broker Quote Email: Update Benefit Highlights PDF Attachment as Link to PDF Repository | 60
RM1068/Virginia transition to state-based exchange | 40
RM1083 Georgia transition to state-based exchange
RM 1054
Total | 435
SMU | 400
Paperless | 255

## Sheet3
PIF Systems
| Jan-May | June RPM Actuals |  | Total
Opex | 842719 | 98940 | 48474.12 | 990133.12
Capex | 1419466 | 206823 | 107214.67 | 1733503.67
2723636.79